## PMO Delivery Data
BFL PMO Delivery Tracker — Q1 FY2026-27 ¦ Copilot in Excel Demo Dataset
Item ID | Portfolio | Portfolio Code | Region | Work Item Type | Project Manager | Raised Date | Closed Date | Actual Days | Planned Days (SLA) | Project Tier | Priority | Status | ➕ Escalation Flag | ➕ Schedule Breach | ➕ Days Open | ➕ Variance Category
PMO-001 | Digital Lending Platform | DLP01 | West | Milestone | Pooja Nair | 1 Jun 2026 | 4 Jun 2026 | 3 | 5 | Tier 2 | Normal | Completed
PMO-002 | Risk & Compliance Tech | RCT02 | West | Change Request | Rahul Sharma | 28 May 2026 | 5 Jun 2026 | 8 | 7 | Tier 3 | High | Completed
PMO-003 | Core Banking Upgrade | CBU03 | Central | Dependency | Anita Desai | 2 Jun 2026 |  |  | 3 | Tier 1 | Normal | In Progress
PMO-004 | Data & Analytics | DNA04 | West | Deliverable | Vikram Joshi | 30 May 2026 | 3 Jun 2026 | 4 | 3 | Tier 4 | Normal | Completed
PMO-005 | Collections Automation | COL05 | West | Risk | Pooja Nair | 25 May 2026 | 6 Jun 2026 | 12 | 7 | Tier 1 | Urgent | Completed
PMO-006 | Governance & Controls | GOV06 | West | Change Request | Anita Desai | 29 May 2026 |  |  | 7 | Tier 5 | High | Escalated
PMO-007 | Enterprise Infrastructure | INF07 | Central | Milestone | Ravi Kumar | 1 Jun 2026 | 5 Jun 2026 | 4 | 5 | Tier 1 | Normal | Completed
PMO-008 | Payments Modernisation | PAY08 | West | Deliverable | Anita Desai | 3 Jun 2026 |  |  | 3 | Tier 2 | Normal | In Progress
PMO-009 | Wealth Platform | WPL09 | Central | Dependency | Rahul Sharma | 31 May 2026 | 4 Jun 2026 | 4 | 3 | Tier 4 | High | Completed
PMO-010 | Digital Lending Platform | DLP10 | West | Change Request | Vikram Joshi | 26 May 2026 | 5 Jun 2026 | 10 | 7 | Tier 5 | Urgent | Completed
PMO-011 | Core Banking Upgrade | CBU11 | West | Risk | Pooja Nair | 27 May 2026 |  |  | 7 | Tier 1 | Normal | In Progress
PMO-012 | Data & Analytics | DNA12 | Central | Milestone | Ravi Kumar | 2 Jun 2026 | 6 Jun 2026 | 4 | 5 | Tier 2 | Normal | Completed
PMO-013 | Risk & Compliance Tech | RCT13 | West | Change Request | Pooja Nair | 24 May 2026 | 4 Jun 2026 | 11 | 7 | Tier 1 | High | Completed
PMO-014 | Collections Automation | COL14 | West | Deliverable | Anita Desai | 1 Jun 2026 | 4 Jun 2026 | 3 | 3 | Tier 4 | Normal | Completed
PMO-015 | Enterprise Infrastructure | INF15 | Central | Dependency | Rahul Sharma | 29 May 2026 | 1 Jun 2026 | 3 | 3 | Tier 1 | Normal | Completed
PMO-016 | Payments Modernisation | PAY16 | West | Change Request | Vikram Joshi | 22 May 2026 | 5 Jun 2026 | 14 | 7 | Tier 2 | Urgent | Completed
PMO-017 | Governance & Controls | GOV17 | West | Risk | Pooja Nair | 3 Jun 2026 |  |  | 7 | Tier 5 | High | Escalated
PMO-018 | Wealth Platform | WPL18 | West | Milestone | Ravi Kumar | 30 May 2026 | 3 Jun 2026 | 4 | 5 | Tier 1 | Normal | Completed
PMO-019 | Digital Lending Platform | DLP19 | Central | Deliverable | Pooja Nair | 2 Jun 2026 |  |  | 3 | Tier 2 | Normal | In Progress
PMO-020 | Data & Analytics | DNA20 | West | Dependency | Rahul Sharma | 28 May 2026 | 2 Jun 2026 | 5 | 3 | Tier 4 | Normal | Completed
PMO-021 | Risk & Compliance Tech | RCT21 | Central | Change Request | Anita Desai | 20 May 2026 | 5 Jun 2026 | 16 | 7 | Tier 5 | Urgent | Completed
PMO-022 | Collections Automation | COL22 | West | Milestone | Vikram Joshi | 31 May 2026 | 4 Jun 2026 | 4 | 5 | Tier 1 | Normal | Completed
PMO-023 | Core Banking Upgrade | CBU23 | West | Risk | Pooja Nair | 1 Jun 2026 |  |  | 7 | Tier 2 | High | In Progress
PMO-024 | Enterprise Infrastructure | INF24 | West | Change Request | Ravi Kumar | 27 May 2026 | 4 Jun 2026 | 8 | 7 | Tier 4 | High | Completed
PMO-025 | Payments Modernisation | PAY25 | West | Deliverable | Pooja Nair | 3 Jun 2026 | 6 Jun 2026 | 3 | 3 | Tier 1 | Normal | Completed
💡 Columns N–Q are empty intentionally. Use Copilot in Excel to add Escalation Flag, Schedule Breach, Days Open, and Variance Category — then build the Pivot Tables.