## Project Portfolio
Project ID | Project Name | Project Manager | Business Unit | Phase | Priority | Start Date | End Date | Planned Duration (Days) | % Complete | Budget (₹ Lakhs) | Spent (₹ Lakhs) | Budget Variance (₹ Lakhs) | Planned Tasks | Completed Tasks | Open Issues | RAG Status | Notes
PRJ-001 | Core Banking Modernization | Anita Sharma | Technology | Execution | High | 01-Jan-2025 | 31-Dec-2025 | 365 | 62 | 850 | 530 | 320 | 48 | 30 | 3 | Green | On track, Phase 2 go-live in Q3
PRJ-002 | Regulatory Compliance Suite | Rajesh Nair | Risk & Compliance | Execution | Critical | 01-Mar-2025 | 30-Sep-2025 | 214 | 45 | 320 | 160 | 160 | 30 | 14 | 7 | Amber | Delay in vendor deliverable - watchlist
PRJ-003 | Data Warehouse Migration | Priya Menon | Data & Analytics | Planning | High | 15-Apr-2025 | 31-Mar-2026 | 351 | 18 | 480 | 90 | 390 | 60 | 11 | 2 | Green | Kick-off done; resource onboarding in progress
PRJ-004 | CRM Platform Upgrade | Vikram Desai | Sales & Distribution | Execution | Medium | 01-Feb-2025 | 31-Aug-2025 | 212 | 70 | 220 | 165 | 55 | 40 | 28 | 5 | Amber | Integration testing delayed by 2 weeks
PRJ-005 | HRMS Self-Service Portal | Sunita Joshi | HR | UAT | Medium | 01-Nov-2024 | 30-Jun-2025 | 241 | 88 | 110 | 100 | 10 | 35 | 31 | 1 | Green | UAT sign-off expected by end of June
PRJ-006 | Cybersecurity Enhancement | Amit Kulkarni | IT Security | Execution | Critical | 01-Jan-2025 | 31-Oct-2025 | 304 | 50 | 600 | 310 | 290 | 50 | 25 | 9 | Red | 3 critical vulnerabilities open; escalated to CISO
PRJ-007 | Mobile Banking App v3 | Neha Kapoor | Digital Banking | Execution | High | 01-Mar-2025 | 30-Nov-2025 | 275 | 40 | 375 | 150 | 225 | 44 | 18 | 4 | Green | Feature freeze planned for Aug
PRJ-008 | ERP Finance Module | Ramesh Iyer | Finance | Initiation | Low | 01-Jun-2025 | 31-May-2026 | 365 | 5 | 290 | 15 | 275 | 20 | 1 | 0 | Green | PMC charter approved; team being formed
PRJ-009 | Cloud Infrastructure Setup | Pooja Tiwari | IT Infrastructure | Execution | High | 15-Feb-2025 | 15-Aug-2025 | 181 | 75 | 520 | 410 | 110 | 36 | 27 | 6 | Amber | Budget overrun risk; mitigation plan in review
PRJ-010 | Customer Analytics Platform | Sanjay Mehta | Data & Analytics | Execution | High | 01-Apr-2025 | 31-Jan-2026 | 306 | 30 | 410 | 125 | 285 | 55 | 17 | 2 | Green | ML model training underway
PRJ-011 | ATM Network Upgrade | Kavita Rao | Operations | Execution | Medium | 01-Mar-2025 | 30-Sep-2025 | 214 | 55 | 180 | 102 | 78 | 30 | 17 | 3 | Green | 30 of 55 ATM locations completed
PRJ-012 | Payment Gateway Integration | Arjun Bose | Payments | Closed | High | 01-Oct-2024 | 31-Mar-2025 | 182 | 100 | 150 | 148 | 2 | 28 | 28 | 0 | Green | Successfully closed; post-implementation review done
PRJ-013 | Fraud Detection AI | Meera Pillai | Risk & Compliance | Execution | Critical | 01-Feb-2025 | 31-Dec-2025 | 334 | 38 | 560 | 215 | 345 | 42 | 16 | 8 | Amber | Model accuracy below threshold; rework in progress
PRJ-014 | Branch Digitization | Deepak Sharma | Operations | Planning | Medium | 01-May-2025 | 30-Apr-2026 | 365 | 10 | 240 | 25 | 215 | 40 | 4 | 1 | Green | Vendor shortlisting ongoing
PRJ-015 | Treasury Management System | Nalini Suresh | Finance | Execution | High | 15-Jan-2025 | 15-Nov-2025 | 305 | 60 | 490 | 300 | 190 | 38 | 23 | 5 | Amber | Integration with Bloomberg feed delayed

## Portfolio Summary
📊 Portfolio Summary Dashboard
📁 Project Overview
Total Projects | 15
Green Status | 9
Amber Status | 5
Red Status | 1
Closed Projects | 1
💰 Budget Overview
Total Budget (₹ Lakhs) | 5795
Total Spent (₹ Lakhs) | 2845
Total Variance (₹ Lakhs) | 2950
Budget Utilization % | 49.1
🚨 Risk & Issues
Critical Projects | 3
Total Open Issues | 56
Projects with Issues > 5 | 4
📅 Delivery Health
Avg % Complete | 49.7
Projects > 75% Complete | 2
Projects < 20% Complete | 3

## Insights Summary
📊 Project Portfolio Insights Summary
🔴 INSIGHT 1: Critical Projects Carry Highest Risk & Issues
The 3 Critical priority projects (Regulatory Compliance, Cybersecurity, Fraud Detection AI) account for ₹1,480 Lakhs (26% of total budget) but have 24 open issues combined—43% of all portfolio issues. The Cybersecurity Enhancement project is the only RED status project with 9 open issues and 3 critical vulnerabilities escalated to CISO.
💰 INSIGHT 2: Low Budget Utilization (49%) Despite Projects Being 50% Through Timeline
Total portfolio budget is ₹5,795 Lakhs with only ₹2,845 Lakhs spent (49.1%). Cloud Infrastructure Setup shows budget overrun risk (₹410L spent at 75% complete on ₹520L budget), while Data Warehouse Migration has significant unspent budget (₹390L variance at only 18% complete). This signals uneven execution pacing across the portfolio.
⚠️ INSIGHT 3: 6 Projects (40%) Are Amber/Red – All in Execution Phase
5 Amber + 1 Red projects represent ₹2,470 Lakhs (43% of budget). All 6 at-risk projects are in Execution phase, suggesting systemic delivery challenges—vendor delays, integration issues, and model accuracy problems. External dependencies are cited as root causes in multiple projects.
🔍 Questions for Deeper Analysis
1. Would you like a timeline/Gantt view of project delivery dates to identify scheduling conflicts?
2. Should we analyze which Project Managers have the most at-risk projects?
3. Would a budget burn-down forecast help identify which projects may exceed budget?
4. Do you want to drill into Business Unit performance (e.g., Risk & Compliance has 2 Amber projects)?
5. Should we create a risk matrix plotting Open Issues vs Budget size to prioritize interventions?

## Project Timeline
📅 Project Timeline / Gantt View
[7 empty] | 45566 | 45597 | 45627 | 45658 | 45689 | 45717 | 45748 | 45778 | 45809 | 45839 | 45870 | 45901 | 45931 | 45962 | 45992 | 46023 | 46054 | 46082 | 46113 | 46143
Project Name | Start | End | Days | %Done | RAG | Phase | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26 | Feb'26 | Mar'26 | Apr'26 | May'26
Payment Gateway Integration | 01-Oct-2024 | 31-Mar-2025 | 182 | 100% | Green | Closed | █ | █ | █ | █ | █ | █
HRMS Self-Service Portal | 01-Nov-2024 | 30-Jun-2025 | 241 | 88% | Green | UAT |  | █ | █ | █ | █ | █ | █ | █ | █
Core Banking Modernization | 01-Jan-2025 | 31-Dec-2025 | 365 | 62% | Green | Execution |  |  |  | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █
Cybersecurity Enhancement | 01-Jan-2025 | 31-Oct-2025 | 304 | 50% | Red | Execution |  |  |  | █ | █ | █ | █ | █ | █ | █ | █ | █ | █
Treasury Management System | 15-Jan-2025 | 15-Nov-2025 | 305 | 60% | Amber | Execution |  |  |  | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █
CRM Platform Upgrade | 01-Feb-2025 | 31-Aug-2025 | 212 | 70% | Amber | Execution |  |  |  |  | █ | █ | █ | █ | █ | █ | █
Fraud Detection AI | 01-Feb-2025 | 31-Dec-2025 | 334 | 38% | Amber | Execution |  |  |  |  | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █
Cloud Infrastructure Setup | 15-Feb-2025 | 15-Aug-2025 | 181 | 75% | Amber | Execution |  |  |  |  | █ | █ | █ | █ | █ | █ | █
Regulatory Compliance Suite | 01-Mar-2025 | 30-Sep-2025 | 214 | 45% | Amber | Execution |  |  |  |  | █ | █ | █ | █ | █ | █ | █ | █
Mobile Banking App v3 | 01-Mar-2025 | 30-Nov-2025 | 275 | 40% | Green | Execution |  |  |  |  | █ | █ | █ | █ | █ | █ | █ | █ | █ | █
ATM Network Upgrade | 01-Mar-2025 | 30-Sep-2025 | 214 | 55% | Green | Execution |  |  |  |  | █ | █ | █ | █ | █ | █ | █ | █
Customer Analytics Platform | 01-Apr-2025 | 31-Jan-2026 | 306 | 30% | Green | Execution | [6 empty] | █ | █ | █ | █ | █ | █ | █ | █ | █ | █
Data Warehouse Migration | 15-Apr-2025 | 31-Mar-2026 | 351 | 18% | Green | Planning | [6 empty] | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █
Branch Digitization | 01-May-2025 | 30-Apr-2026 | 365 | 10% | Green | Planning | [6 empty] | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █
ERP Finance Module | 01-Jun-2025 | 31-May-2026 | 365 | 5% | Green | Initiation | [8 empty] | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █
📍 Today: May 28, 2025
Legend: | █ Green | █ Amber | █ Red
⚠️ Scheduling Observations
• Peak Overlap (Mar-Sep 2025): 11 projects running concurrently — high resource contention risk
• Q3 2025 Crunch: 6 projects ending Aug-Oct including 2 Critical priority — potential delivery bottleneck
• At-Risk Projects (Amber/Red): All concentrated in execution phase with overlapping timelines
• Long-running projects (Data Warehouse, ERP Finance, Branch Digitization) extend well into 2026